## Gantt chart
AD 17
Work packages | Responsible | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
1. Generate a voxel grid representation of the environment | Sergio Zerpa
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation | bar: W24
Generate a point cloud from depth image | bar: W25
Generate occupancy grid from point cloud | bar: W25
Merge the voxel grid representation into a global map | bar: W26
Improve quality taking driftting into consideration and ntegrate into whole system | bar: W26 to W27
Prepare final report, code comments and code refactoring | bar: W30
2. Object detection | Cuong Van Dam
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation | bar: W24
Extract the position/pixels of each class (trafic light, cars, pedestrians, road) from the semantic segmentation map. | bar: W25 to W26
Combine information with the depth camera information. | bar: W25 to W26
Combine RGB camera with semantic segmentation map to extract the RGB bounding box for the traffic light | bar: W27 to W28
Build traffic light classification model- red,green,yellow- or just use opencv to detect color | bar: W29
Prepare final report, code comments and code refactoring | bar: W30
3. Path planning (Geometric representation of a route, high-level route information) | Jesco Melzer
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation | bar: W24
Implementation of less then 10 goal points | bar: W25 to W26
Implementation of OMPL (Open Motion Planning Library) | bar: W27 to W28
Integration | bar: W29
Prepare final report, code comments and code refactoring | bar: W30
4. Trajectory planning | Maxime Kleinhans and Mohammadali Rahmati
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation (DWA) | bar: W24
Generate the car path manually | bar: W25
Writing Node collision probabilities and trajectory generator | bar: W26 to W28
Incorporate performance metrics | bar: W29
Prepare final report, code comments and code refactoring | bar: W30
5. Control and FSM | Sergio Zerpa and team
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation | bar: W27
Implement a motion control algorithm to regulate acceleration, braking, and steering rate. | bar: W27
Incorporate a state machine to manage traffic lights (and road rules) | bar: W28
Improve performance of whole system | bar: W29
Prepare final report, code comments and code refactoring | bar: W30