## Gantt chart
TEAM 17 - AUTONOMOUS DRIVING
Work packages | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
1. Generate a voxel grip representation of the environment
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation | bar: W24
Generate a point cloud from depth image | bar: W25
Generate occupancy grid from point cloud | bar: W25
Merge the voxel grid representation into a global map | bar: W25
Integrate into whole system | bar: W26
Prepare final report, code comments and code refactoring | bar: W30
2. Object detection
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation | bar: W24
Process info from semantic camera to extract a list of detections (i.e. car, traffic light …) | bar: W25 to W26
Process info from semantic camera to extract relevant segmentation information | bar: W27 to W28
Integrate detections and segmentation into global map? and/or add timestamp info and pose info? | bar: W29
Prepare final report, code comments and code refactoring | bar: W30
3. Path planning (Geometric representation of a route, high-level route information)
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation (SLAM?) | bar: W24
Implementation part 1 | bar: W25 to W26
Implementation part 2 | bar: W27 to W28
Integration | bar: W29
Prepare final report, code comments and code refactoring | bar: W30
4. Trajectory planning
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation (CTRA model, encoder-decoder?) | bar: W24
Implementation part 1 | bar: W25 to W26
Implementation part 2 | bar: W27 to W28
Incorporate performance metrics? (Collision probabilities?) | bar: W29
Prepare final report, code comments and code refactoring | bar: W30
5. Control and FSM
Getting familiar with base code (run simulation, create a rostra of messages) | bar: W23
Research methods and algorithms for implementation | bar: W24
Implement a motion control algorithm to regulate acceleration, braking, and steering rate. | bar: W27
Incorporate a state machine to manage traffic lights (and road rules like …?) | bar: W28
Improve performance of whole system | bar: W29
Prepare final report, code comments and code refactoring | bar: W30